## 00_README
VELOOP Rewards — Deliverable 13: Data Quality Audit
Project | Data Analyst Internship — Task 01
Prepared by | Jiya Tejwani — Data Analyst Intern
Date | 2026-10-20
Data status | All figures below are derived from SIMULATED / FICTIONAL data created for analytical testing. They are NOT actual VELOOP users, performance, or statistics and must never be represented as such.
Scope | The two intentionally-messy sheets (Users_Messy_Audit, 10_Event_Data_Quality_Audit) plus cross-field and cross-file validity checks on the clean sheets.
Severity scale | Critical = blocks reliable analysis / cross-dataset joins · High = double-counting or wrong metrics · Medium = parsing/grouping errors, fixable at ingestion · Low = expected/by-design sparsity, monitor only.
How to read | 01_Issue_Register is the formal audit (task's required schema). 02_Evidence_Samples shows offending records. 03_DQ_Scorecard scores each dataset on 5 quality dimensions.
Key point | Quality problems are concentrated in the *_Audit sheets by design. The clean operational sheets passed logical-consistency tests (0 completed-but-uncredited tasks, 0 negative durations, 0 orphan keys).

## 01_Issue_Register
Data Quality Issue Register
Required audit schema per Work Package K. All figures below are derived from SIMULATED / FICTIONAL data created for analytical testing. They are NOT actual VELOOP users, performance, or statistics and must never be represented as such.
Issue_ID | Dataset | Field | Issue_Type | Records_Affected | Severity | Detection_Logic | Likely_Cause | Correction | Prevention | Owner | Status
DQ-01 | Users_Messy_Audit | user_id | Duplicate IDs | 16 | High | user_id.duplicated(keep=False) → 8 IDs repeated | Re-ingestion / merge without dedup key | De-duplicate on user_id keeping latest record; enforce unique constraint | Enforce PRIMARY KEY(user_id) at ingestion; reject/merge duplicates | Engineering / Data | Open
DQ-02 | 10_Event_Data_Quality_Audit | event_id | Duplicate events | 20 | High | event_id.duplicated(keep=False) → 10 event_ids repeated | At-least-once event delivery without idempotency | Deduplicate on event_id before loading analytics layer | Idempotent event ingestion keyed on event_id; dedup window | Engineering | Open
DQ-03 | Users_Messy_Audit | registration_datetime | Malformed date | 1 | High | to_datetime(errors=coerce) fails on value '2026-14-02 12:00' | Free-text date entry / wrong month field (month=14) | Reject at validation; standardise to ISO-8601 UTC | Schema-enforced datetime type + range check at collection | Engineering | Open
DQ-04 | Users_Messy_Audit | registration_datetime | Inconsistent data type | 1008 | Medium | Column dtype is text in messy sheet vs datetime in clean | Mixed string/date values force whole column to text | Cast to datetime after cleaning malformed values | Typed columns enforced in raw + analytics layers | Data | Open
DQ-05 | 10_Event_Data_Quality_Audit | feature_name | Inconsistent capitalization | 5 | Medium | feature_name not in canonical Title-Case set; variants: daily reward, leaderboard, missions, wallet, watch ads | Client sends feature label as free text | Map to controlled vocabulary (Title Case) before grouping | Controlled enum for feature_name; validate at ingestion | Engineering / Data | Open
DQ-06 | Users_1000_Clean | days_since_registration | Impossible value (negative) | 4 | Medium | days_since_registration < 0 found 4 row(s) | Registration timestamp in the future / clock skew | Recompute from server-authoritative UTC timestamps | Server-side timestamps only; reject future-dated events | Engineering | Open
DQ-07 | Users_Messy_Audit | age/gender/city/acquisition_source/primary_device/verification/onboarding | Unexpected nulls in core fields | 7 | Medium | isna() on core columns → 1 null each in: age, gender, city, acquisition_source, primary_device, email_verification_status, onboarding_status | Dropped values during capture/merge | Backfill where source-of-truth exists; flag Required fields | NOT NULL on required fields; capture-time validation | Data / Product | Open
DQ-08 | Users_Messy_Audit | (row grain) | Extra / inconsistent row count | 8 | Medium | Messy sheet has 1008 rows vs 1000 clean | Duplicates inflate the user table | Reconcile to 1,000 distinct users after dedup | Row-count reconciliation checks in pipeline | Data | Open
DQ-09 | File 1 ↔ File 2 | user_id | Cross-file identity mismatch | 1000 | Critical | 0 of 1,000 shared user_ids map to the same full_name across files | Two independent synthetic populations reuse one ID scheme | Do NOT join across files on user_id; keep datasets separate or re-key | Single source of truth for user identity; global stable user_id | Data / Product | Open
DQ-10 | (cross-dataset) | Rewards/Wallet/Withdrawals/Referrals | Missing critical entities | 4 entities | Critical | No transaction-grade table for reward ledger, wallet, withdrawals or referral lifecycle | Product areas not yet instrumented | Design & instrument the proposed entities (see Data Model / Event Plan) | Event tracking plan + schema before launch of each feature | Product / Engineering | Open
DQ-11 | (all monetary KPIs) | amount / currency | No monetary amount field | 0 fields | High | No column represents credit value, redemption value or payout amount | Monetisation not instrumented | Add amount + unit + currency to reward/wallet/withdrawal schemas | Mandatory amount+unit on every value-bearing event | Product / Engineering | Open
DQ-12 | Users_1000_Clean | last_login_datetime | Sparse by design | 72 | Low | NULL where user has never logged in | Expected for never-active users | Keep NULL; interpret as 'no login' not missing data | Document nullable-by-design fields in dictionary | Data | Accepted
DQ-13 | 02_Sessions | exit_feature | Sparse by design | 466 | Low | NULL where session had no distinct exit feature | Expected for very short sessions | Keep NULL; exclude from exit-feature breakdowns | Documented nullable field | Data | Accepted
DQ-14 | 06_Milestones | session_id | Sparse by design | 40 | Low | NULL where milestone is not session-bound | Expected (e.g. day-count milestones) | Keep NULL; milestone FK to session is optional | Documented optional FK | Data | Accepted

## 02_Evidence_Samples
Evidence Samples
All figures below are derived from SIMULATED / FICTIONAL data created for analytical testing. They are NOT actual VELOOP users, performance, or statistics and must never be represented as such.
Issue | Evidence
DQ-01 duplicate user_ids | IDs appearing more than once: VLUSR000095, VLUSR000217, VLUSR000272, VLUSR000335, VLUSR000409, VLUSR000779, VLUSR000803, VLUSR000813
DQ-02 duplicate event_ids | event_ids appearing more than once: EVT00006040, EVT00006379, EVT00011275, EVT00014772, EVT00017051, EVT00021600, EVT00025552, EVT00028196, EVT00030205, EVT00034075
DQ-03 malformed date | Raw value(s): 2026-14-02 12:00
DQ-05 casing variants | Non-canonical feature_name values: daily reward, leaderboard, missions, wallet, watch ads
DQ-06 negative days_since_registration | user_id=VLUSR000128 registered=2026-09-15 11:07:00 last_login=2026-09-16 17:07:00 days_since=-0.5
DQ-07 core-field nulls (messy) | age=1 null; gender=1 null; city=1 null; acquisition_source=1 null; primary_device=1 null; email_verification_status=1 null; onboarding_status=1 null

## 03_DQ_Scorecard
Data Quality Scorecard by Dataset (5 dimensions)
Completeness & ID-Uniqueness are % (higher=better). All figures below are derived from SIMULATED / FICTIONAL data created for analytical testing. They are NOT actual VELOOP users, performance, or statistics and must never be represented as such.
Dataset | Completeness | ID_Uniqueness | Validity | Consistency | Referential | Overall
File1 Users_1000_Clean | 96.47 | 100 | 1 impossible days_since value | OK | n/a (standalone) | Good (minor validity)
File1 Users_Messy_Audit | 96.58 | 99.21 | 1 malformed date; type drift | dup rows | n/a | Poor (intentional)
File2 01_Users_1000 | 94.71 | 100 | OK | OK | parent table | Good
File2 02_Sessions | 99.51 | 100 | OK | OK | 100% users matched | Good
File2 03_Feature_Events | 100 | 100 | OK | OK | 100% user+session matched | Excellent
File2 05_Task_Activity | 91.12 | 100 | status↔reward logic OK | OK | 100% matched | Good
File2 10_Event_DQ_Audit | 100 | 99.97 | casing variants | dup events | 100% matched | Poor (intentional)