## 00_README
VELOOP Rewards — Deliverable 19: Source & Verification Register
Project | Data Analyst Internship — Task 01 (Section 6 + Work Package S)
Prepared by | Jiya Tejwani — Data Analyst Intern
Date | 2026-10-21
Data status | All figures derived from SIMULATED / FICTIONAL data created for analytical testing. They are NOT actual VELOOP users, performance, or statistics and must never be represented as such.
Purpose | Mandatory integrity control: every important product fact or unknown is recorded here instead of being silently assumed, separating verified facts from assumptions and proposed requirements.
Columns | Follows Section 6 (Information, Source, Source Type, Date Checked, Status, Notes) and Work Package S (ID, Unknown, Why It Matters, Risk, Verification Owner).
Source types | Official (public VELOOP source) · Internal (the task brief) · Simulated (derived from the supplied fictional dataset).
Status key | Confirmed = verified from an available source · To-Be-Verified = assumed/partial, needs engineering or product confirmation · Proposed = does not exist today and must be designed.
Discipline | No assumption is presented as a fact. Example: session_id is recorded as a present/proposed analytics field whose production status requires engineering verification — never as 'VELOOP stores a session ID for every user'.
Tabs | 01 Source & Verification Register

## 01_Source_Verification_Register
Source & Verification Register
Records what is known, what is assumed, and what is unverified. All figures derived from SIMULATED / FICTIONAL data created for analytical testing. They are NOT actual VELOOP users, performance, or statistics and must never be represented as such.
ID | Item or Unknown | Why It Matters | What Was Found | Source | Source Type | Date Checked | Status | Risk | Verification Owner | Notes
SR-001 | Does VELOOP emit task-completion events in production? | Task analytics (completion & failure KPIs) depend on it | Task_Activity sheet exists in simulated data; live instrumentation unconfirmed | Simulated dataset | Simulated | 2026-10-20 | To-Be-Verified | High | Engineering | Design assumes it; must be engineering-verified before relying on it
SR-002 | Is there a stable, app-wide user_id across devices & features? | All cross-dataset joins and per-user metrics depend on it | Two supplied files reuse the same IDs for different people | Simulated dataset | Simulated | 2026-10-20 | To-Be-Verified | High | Engineering | Single source of truth for identity needed before joins
SR-003 | Which reward currencies are live (XP, Gems, Tokens, Spins)? | Reward & economy KPIs must know which currencies exist | XP present; Gems/Tokens/Spins named in brief but absent from data | Brief + simulated data | Internal + Simulated | 2026-10-20 | To-Be-Verified | Medium | Product | Do not assume all currencies are implemented
SR-004 | Does a wallet transaction ledger exist? | Wallet volume/balance analytics cannot exist without it | No wallet transaction table; Wallet is only a UI feature in events | Simulated dataset | Simulated | 2026-10-20 | Proposed | Critical | Engineering | Must be designed; no amounts/balances today
SR-005 | Does a withdrawal / payout system & data exist? | Entire withdrawal funnel & payout KPIs depend on it | No withdrawal records of any kind in the data | Simulated dataset | Simulated | 2026-10-20 | Proposed | Critical | Engineering + Payments | Entirely absent; whole lifecycle must be designed
SR-006 | Is the referral lifecycle captured (referrer -> referred -> conversion)? | Referral conversion KPIs require referrer->referred linkage | Only acquisition_source='Referral', referral_source_detail, referral_code exist | Simulated dataset | Simulated | 2026-10-20 | Proposed | High | Engineering | No referrer->referred linkage table
SR-007 | Are monetary amounts / units recorded on value events? | Every value / volume / revenue KPI is blocked without it | No amount or currency-unit field exists anywhere | Simulated dataset | Simulated | 2026-10-20 | Proposed | Critical | Product + Engineering | Blocks all monetisation KPIs
SR-008 | Are session identifiers reliable for session analytics? | Session-level analytics rely on it | session_id present in file 2; passes referential-integrity tests | Simulated dataset | Simulated | 2026-10-20 | Confirmed | Low | Analytics | Usable for session analysis within file 2 only
SR-009 | Are third-party provider identifiers captured for ads/surveys/offers? | Crediting-reliability analysis needs external references | No provider_id / external_txn_id / callback fields present | Simulated data + brief (C4) | Simulated | 2026-10-20 | Proposed | High | Engineering | External systems affect crediting reliability
SR-010 | What event-naming convention is used in production? | Consistent event names keep metrics from splitting | Sim uses object_action-style names; production unconfirmed | Simulated dataset | Simulated | 2026-10-20 | To-Be-Verified | Medium | Engineering | Propose a standard; confirm adoption
SR-011 | Is account status-change history recorded? | Churn / suspension analysis needs state transitions | Only current account_status; no status-change log | Simulated dataset | Simulated | 2026-10-20 | Proposed | Medium | Engineering | Needed for churn / risk analysis
SR-012 | Is a verification timestamp captured? | Verification-funnel timing needs a timestamp | Only verification_status; no verified_at | Simulated dataset | Simulated | 2026-10-20 | To-Be-Verified | Medium | Engineering | Needed for verification funnel
SR-013 | Are onboarding step-level events captured? | Activation funnel & drop-off step need step-level events | Only onboarding_status (Not Started/Started/Completed) | Simulated dataset | Simulated | 2026-10-20 | To-Be-Verified | High | Product + Engineering | Needed for an activation funnel
SR-014 | Is streak length recorded? | Streak distribution & retention analysis need the value | Only a streak_activity Yes/No flag in daily rollup | Simulated dataset | Simulated | 2026-10-20 | Proposed | Medium | Engineering | Need the actual streak length value
SR-015 | What geography does the product cover? | Determines geographic-segmentation scope | Users are India-only; state distributions differ across files | Simulated dataset | Simulated | 2026-10-20 | Confirmed | Low | Analytics | Single-country simulation
SR-016 | What platforms are supported? | Determines platform-segmentation & roadmap scope | platform='Web' for all rows; no native-app platform present | Simulated dataset | Simulated | 2026-10-20 | To-Be-Verified | Medium | Product | Confirm whether native apps exist
SR-017 | Are reward reversal / correction records kept? | Fraud/error and reward-reversal KPIs depend on it | None present in the data | Simulated dataset | Simulated | 2026-10-20 | Proposed | High | Engineering | Needed for fraud and error handling
SR-018 | What is the data refresh cadence / pipeline? | Dashboard freshness & pipeline design depend on it | Unknown; the simulated set is a static snapshot | Simulated dataset | Simulated | 2026-10-20 | To-Be-Verified | Medium | Data Engineering | Pipeline & refresh must be defined
SR-019 | What is the consent & marketing-opt-in model? | Governance & marketing-eligibility gating depend on it | consent_status and marketing_opt_in exist in file 1 | Simulated dataset | Simulated | 2026-10-20 | To-Be-Verified | Medium | Legal + Product | Confirm consent model for governance
SR-020 | Is event ingestion idempotent in production? | Prevents duplicate-event double counting | Audit sheet contains duplicate event_ids (10 ids / 20 rows) | Simulated dataset | Simulated | 2026-10-20 | To-Be-Verified | High | Engineering | Need idempotent, dedup-keyed ingestion
SR-021 | Which product features are live vs planned? | Avoids measuring features that are not implemented | Brief lists many areas; data shows 15 concrete features | Brief + simulated data | Internal + Simulated | 2026-10-20 | To-Be-Verified | Medium | Product | Do not assume every feature is implemented
SR-022 | Is there an authoritative public spec for VELOOP instrumentation? | Determines how much product detail can be treated as verified | No authoritative public product documentation was available | Public web (searched, not found) | Official (absent) | 2026-10-20 | To-Be-Verified | Low | Product | Treat all product-implementation detail as unverified